## Start Here
Objective | This workbook provides a structured framework for defining your annual Go-to-Market (GTM) plan. The outputs from these tabs will serve as the direct inputs for configuring your Fullcast environment and preparing to cutover between your current and next year's plan. Instructions for Use 1. Complete all tabs sequentially: Each tab builds on the previous one, from high-level targets to granular assignments. 2. Document assumptions: Use the 'Issues & Q's' tab to log all key business assumptions, dependencies, or open questions that arise during your planning process. Use this to track progress and action items with your CSM. 3. Review and finalize: The completed workbook represents the final plan design to be implemented in Fullcast.
General Planning Timeline | A templated timeline with key milestones for the annual planning process. Adjust dates to fit your fiscal year.
Discovery Questions | A series of foundational questions to align stakeholders on the strategic goals, segmentation logic, and rules of engagement for the upcoming year.
Go Live Run List | A sequential checklist of technical and operational tasks required to ensure a successful cutover to the new plan in the Fullcast production environment.
Issues & Questions | Use this tab as a centralized log to track open questions, critical assumptions, potential risks, and required decisions throughout the planning process.

## Discovery Questions
Discovery Questions | Notes
Timeline
What is the date for the planned cutover to the new fiscal year?
When do you expect first input on territory changes?
How many revisions of the plan do you anticipate?
Organizational changes
Are you adding or removing any roles/overlays?
New metrics
What new metrics will you use for balancing?
Territory changes
What are the key metrics that will be used for carving territories?
Are you adding any new markets?
Are you adding any new GTM teams like a vertical or global
Are you changing any segmentation lines?
Policy changes
Are you changing any rules in your holdout policy?
Project variables
Is there a data enrichment project happening prior to GTM planning?
Are there any other GTM changes for the next year?
Flows and automations
Do we have a complete list of all automations triggered by the Fullcast export? Account Teams, etc.
The Fullcast cutover export will replace the entire account team on every account. What will be the impact in SF?
Should we consider doing a data load to replace those automations at export? Consider advantages over SF flows.

## General Planning Timeline
Column 4 | Phase | Days before go-live | Due Date
FALSE | Data enrichment | 150 | 2025-08-05
FALSE | Validate metric calculations and import fields | 120 | 2025-09-04
FALSE | Capacity planning | 120 | 2025-09-04
FALSE | Baseline territory planning | 90 | 2025-10-04
FALSE | Build out teams for quota planning | 90 | 2025-10-04
FALSE | Set tops down quota | 90 | 2025-10-04
FALSE | Assignments of current reps | 60 | 2025-11-03
FALSE | Assignment of TBH | 60 | 2025-11-03
FALSE | Bottoms up quota | 45 | 2025-11-18
FALSE | Review of current rep territories with sales leaders | 45 | 2025-11-18
FALSE | Review of holdout policy | 45 | 2025-11-18
FALSE | Confirm date for cutover, set appt on calendar | 45 | 2025-11-13
FALSE | Involve customer SF admin team in planning process, impacts | 45 | 2025-11-13
FALSE | Adjustments to quota by sales leaders | 30 | 2025-12-03
FALSE | Align with SFDC and IT teams to understand downstream impacts of Fullcast cutover | 30 | 2025-12-03
FALSE | Routing review | 30 | 2025-12-03
FALSE | Review export job configuration | 30 | 2025-12-03
FALSE | Review auto rerun rules settings | 10 | 2025-12-23
FALSE | Confirm who from both Fullcast and customer team will be online during cutover and the escalation plan | 10 | 2025-12-23
FALSE | Final review and approval (minor account moves ok after this, but major structural changes will cause delays to go live) | 5 | 2025-12-28
FALSE | Go Live | 0 | 2026-01-02 | << Insert go-live date in this cell
Formulas:
Due Date = D23-[Days before go-live]
Due Date = [Due Date, row below]-[Days before go-live]

## Go Live Run List
💡TIP: Click the calculator icon below to toggle to a view that includes only the territory-related steps!
Complete? | Step | Time | System | Relevant Modules | Details | Documentation
FALSE | Review original Fullcast go-live notes | 1 Month Prior | Salesforce | Territories | Ensure your Salesforce team is involved and prepared for the Fullcast cutover. Add any specific items for your organization to this run list.
FALSE | Mass update assignment end dates | As needed | Fullcast | Territories | Ensure there are no lapses in coverage if your cutover date gets pushed out beyond the end of your current fiscal year | Mass update assignments
FALSE | Commit all changes | 1 Day Prior | Fullcast | Territories | Make sure that all changes that need to be pushed will get pushed. | Use a "review proposed changes" saved view
FALSE | Validate coverage ssignments | 1 Day Prior | Fullcast | Territories | Review territory coverage assignments in your new plan. Ensure all territories have the intended coverage. | Create a coverage report
FALSE | Simulate export | 1 Day Prior | Fullcast | Territories | Review all of the records that will be upserted and deleted if the import were run at that moment. | Simulate a 'migrate all' export job
FALSE | Validate policies have been created in new plan | 1 Day Prior | Fullcast | Policies | Review the active policies in the current plan and ensure they're all present in the new plan.
FALSE | Temporarily disable any flows or notifications in Salesforce | Day of | Salesforce | Territories | If Fullcast exports trigger any flows, notifications, etc., consider disabling them.
FALSE | Backup account data | Day of | Salesforce | Territories | Best practice for any mass data update.
FALSE | Disable old plan for export | Day of | Fullcast | Territories | Turn off the export for your current year plan. Be sure to do this before enabling export on your new plan. | Configure plan export settings
FALSE | Enable new plan for export | Day of | Fullcast | Territories | Enabling the export in the plan settings does not initiate an export job.
FALSE | Enable roles for export | Day of | Fullcast | Territories | Confirm which roles are exporting to the account team. | Manage roles and toggle on/off the export
FALSE | Export to SFDC | Day of | Fullcast | Territories | Run a migrate all job. This is critical to ensure the apropriate cleanup happens. | Run an ad hoc export job
FALSE | Monitor job | Day of | Fullcast | Territories | As the export progresses, you can view it in Fullcast. You can see information such as the number of records processed at each stage of the job. | Review job status
FALSE | Troubleshoot job issues | Day of | Salesforce | Territories | When cutting over between plans, there are a few common issues that stem from the Salesforce side. | Troubleshoot article - draft ready for review
FALSE | Enable policies in new plan | Day of | Fullcast | Policies |  | Activate and deactivate policies
FALSE | Disable policies in old plan | Day of | Fullcast | Policies
FALSE | Spot test policies in Prod | Day of | Fullcast | Policies

## Issues & Questions
Date | Name | Status | Question (anything that needs to be addressed) | Answer